## Sheet1
Name | Omar Arias, Josh L, Marcos
Project | Grocery Store
For each part of the project as you start to work on it break the project into tasks. Estimate how long you expect each task to take. Turn in the estimate. When you turn in your project also include the results of the estimate. The formula to calculate the sum of a set of numbers: =sum(cell1 : lastcell), example =sum ( B5 : b10 ), the formula would probably go into cell B11.
| task | estimated time | actual time | difference | discrepency
Part 1
Decide what items will be sold
Create a class with 5 data members
Create a driver class
Create an object
Create a text file
total |  | 4 hours | 1.5 hours | 2.5 hours | 2.5 hours less
Part 2
Add constructors, getters and setters
Add a method to input
total |  | 4 hours | 2 hours | 2 hours | 2 hours less
Part 3
Create an array
Read in text file
Allow users to add additional items
Output information from the array
Total |  | 4 hours | 2.5 hours | 1.5 hours | 1.5 hours less
Part 4
Create a menu
Total |  | 4 hours | 2 hours | 2 hours | 2 hours less
Part 5
Have individual customers buy items
keep track of inventory
Output if item is out of stock
keep track of items that could have been sold if items were in stock
Output customer's total
Total |  | 4 hours | 5.75 hours | 1.75 hours | 1.75 hours longer
Part 6
Have customers be part of a group with a single bill
Total |  | 4 hours | 3.5 hours | 0.5 hours | Half hour less
Part 7
Create a manager's report
Display inventory after password is typed in
Show inventory, sales for the day, sales that could have been made if item was in stock
Let manager buy for inventory, store values back into the file
Total |  | 6 hours | 7 hours | 1 hour | 1 hour longer
Part 8
Record customer's order
Output customer's order
Allow customer to make changes
Total |  | 4 hours | 3 hours (unsuccessful) | 1 hour | 1 hour less (incomplete)